## Sheet1
Item | Topics | Feedback | Status | Action summary
1 | FGU, FDO intransit/intransit data for direct ship parts. | Intransit data missing for discrete order shipment to DF | Open | - Mandy working with Amit for long term solution; - Short term solution: Use smartsheet as workaround to put in the missing intransit data
2 | How to enable PSP to access data and self serve on supply allocation analysis | 1. Enable user download lastet supply file in allocation tool, under working, firewall issue 2. Users can manual adjust supply commit upon needed 3. Re-run allocation result with updated number | Open | Ken working with InfoSec team for access. ETA: Dec 10
3 | More flexibility on priority selection based on SSD, FCD target. | 1.Only current view available based on real busienss needs 2. Check if revenue view possible for QE | Open | - To be discussed if different logic needed; - Propose to add in to consider YE orders following Current FCD
4 | MPQ | Data available in SCDX, need further alignment business needs | Open | - To be further discussed/aligned
5 | Allocation proposal for the following week output/EDI recovery allocation | Long term discussion | Open | - To be further discussed/aligned for EDI allocation need and logic
6 | 3A4 download view | Ken share view to users in UOV | Closed
7 | 7,14,21 days backlog view added | To add 7days, 14days, 21days, supply, backlog, gap, against target SSD | Closed
8 | Group PN discussion for WNBU, based on DF org allocation for PCBA build. | Smart sheet enabled for manual adjustment | Closed